## Sheet1
Execution ID | Test Case ID | Module | Tester | Execution Date | Expected Result | Actual Result | Status | Bug ID | Remarks
EXE-001 | TC-001 | Login | Isha Pawar | 2026-06-28 | User should login successfully | User logged in successfully | Pass | - | Working as expected
EXE-002 | TC-002 | Login | Isha Pawar | 2026-06-28 | Error message should be displayed | User logged in with invalid password | Fail | BUG-001 | Authentication issue
EXE-003 | TC-007 | Login | Isha Pawar | 2026-06-28 | Password should be masked | Password visible | Fail | BUG-002 | Security issue
EXE-004 | TC-REG-001 | Registration | Isha Pawar | 2026-06-28 | Account should be created | Account created successfully | Pass | - | Working correctly
EXE-005 | TC-REG-002 | Registration | Isha Pawar | 2026-06-28 | Duplicate email should not register | Duplicate account created | Fail | BUG-003 | Validation missing
EXE-006 | TC-UP-001 | File Upload | Isha Pawar | 2026-06-28 | PDF file should upload | File uploaded successfully | Pass | - | Working correctly
EXE-007 | TC-UP-003 | File Upload | Isha Pawar | 2026-06-28 | File larger than 100 MB should be rejected | Large file uploaded successfully | Fail | BUG-005 | File size validation missing
EXE-008 | TC-DWN-001 | File Download | Isha Pawar | 2026-06-28 | File should download successfully | File downloaded successfully | Pass | - | Working correctly
EXE-009 | TC-REN-001 | Rename File | Isha Pawar | 2026-06-28 | File should be renamed | File renamed successfully | Pass | - | Working correctly
EXE-010 | TC-DEL-001 | Delete File | Isha Pawar | 2026-06-28 | File should be deleted | File deleted successfully | Pass | - | Working correctly
EXE-011 | TC-SEA-001 | Search | Isha Pawar | 2026-06-28 | Matching file should be displayed | File displayed successfully | Pass | - | Working correctly
EXE-012 | TC-SEA-004 | Search | Isha Pawar | 2026-06-28 | Search should be case-insensitive | No results returned | Fail | BUG-010 | Search functionality issue
EXE-013 | TC-PRO-002 | Profile | Isha Pawar | 2026-06-28 | Profile should update successfully | Profile updated successfully | Pass | - | Working correctly
EXE-014 | TC-LOG-001 | Logout | Isha Pawar | 2026-06-28 | User should logout successfully | User logged out successfully | Pass | - | Working correctly
EXE-015 | TC-LOG-002 | Logout | Isha Pawar | 2026-06-28 | Dashboard should not be accessible | Dashboard accessible after logout | Fail | BUG-014 | Session handling issue